## (AF) Action Register
| ACTION REGISTER |  | Hedland Community Safety Advisory Forum |  | Count of entries (filter) | 32 |  | Today | 2018-09-03 | Last entry | 2018-08-21
| No. | Action point | Description | Status / ongoing activities | Startegic Goal | Owner / responsibility | Priority | Date identified | Due date | Date closed | Status
| 17 | AOD Plan | Kevin Michel sent a request to the Commisioners office on the local Alcohol and Other Drug plans. To date he has not received a response and will continue to report back to the group in this space. | In progress | Port Hedland AOD-VSU Plan | Department of Communities | Low | 2018-04-30 | 2018-08-14 |  | overdue
| 20 | Safe House | Suggested that Julyardi Aboriginal Corporation representative present information on the concept of establishing a safe house for young people. This agenda will be deffered until further notice. | To be put on hold, until further notice. | To support families, children and young people | Hedland Aboriginal Strong Leaders | Low
| 24 | WA Police Lobbying- FTE Position | Mayor Blanco to lobby on behalf of Advisory Forum for increased FTE Domestic Violence Position in South Hedland Police Station. Moved: Lincoln Tavo Seconded: Jeanette Hasleby | Letter in Progress | Good Governance and Civic Leadership | Town of Port Hedland | High | 2018-06-11 | 2018-08-21 |  | overdue
|  |  | Hedland Aboriginal Strong Leaders to complete a support letter for the Mayor to advocate for the FTE position. | Letter in progress | Good Governance and Civic Leadership | Hedland Aboriginal Strong Leaders | High | 2018-06-11 | 2018-08-21 |  | overdue
| 25 | JD Hardie Capacity Building and Expansion | The Advisory Forum supports the expansion and capacity building of the JD Hardie Centre Masterplan | In progress | Good Governance and Civic Leadership | Hedland Community Safety Advisory Forum | High | 2018-06-11 | 2018-08-14 |  | overdue
| 26 | Youth Diversionary | The Advisory Forum identified one of their focus areas moving forward as a short term goal would be Youth Diversionary. The Town of Port Hedland will facilitate this space moving forward and if need be will setup a sub-working group. | In progress | To support families, children and young people | Town of Port Hedland | Medium | 2018-06-11 | 2018-08-21 | 2018-08-21 | closed
| 27 | Alcohol | The Advisory Forum identified one of their focus areas moving forward as a short term goal would be Alcohol and identifying baseline local data. A sub committee would be established. WAPOL, DSS, FMGL, Town of Port Hedland | In progress | To support families, children and young people | Town of Port Hedland | High | 2018-06-11 | 2018-08-21 | 2018-08-21 | closed
| 28 | s52 proces | WAPOL and CPFS to provide a presentation outlining the process of the current s52 application process. Outlining the legislative requirements, barriers to applying and gaps in the system. What are the positives of this process and how does in impact the community i.e. increase in street drinking but providing a safe home environment for children? Hedland Aboriginal Strong Leaders to voice cultural considerations and barriers to the application process. | Not started | Good Governance and Civic Leadership | Advisory Forum & Action Group | High | 2018-08-21 | 2018-10-02 |  | due in 29 days
| 29 | Banned Drinkers Register | Nomination of a sub group to write a letter to Minister Papalia on par-taking in the consultation of the implementation plan for the register. Nominated members: Dept. Health, CPFS, WAPOL, Industry, Hedland Aboriginal Strong Leaders, non-government representative. Community Safety Advisor to organise sub-group meeting. | In progress, Community Safety Advisor seeking advice and direction from Minister Papalia's Senior Policy Advisor, Emma Roebuck. | Good Governance and Civic Leadership | Sub-group | High | 2018-08-21 | 2018-10-02 |  | due in 29 days
| 30 | VSU | CPFS has noted there has been a spike in VSU in Hedland and wider communities. A coordinated approach is required to combating this spike as previously done. | Statement | To identify and tackle priority offences in Port Hedland | Dept. Communities- CPFS | High | 2018-08-21 | 2018-08-21 | 2018-08-21 | closed
|  | Youth Diversionary | Request for Dept. Education to provide updated school attendance rates for Hedland. | Not started- please refer to meeting notes tab for school attendance dates from 2015-2017. | To identify and tackle priority offences in Port Hedland | Dept. Education- Pilbara | Low | 2018-08-21 | 2018-10-02 |  | due in 29 days
| 1 | Stage One: Mapping analysis | All members to provide a basic scope on the services they fund and operate pertaining to Community Safety and Crime Prevention Services. (Please refer to Core Areas tab below for further clarity) | Information received by BHP Billiton, Dept of Education and Dept Social Services. Responses received by Dept. Human Services, PMC, Roy Hill, Rio Tinto. Findings to be discussed in next meeting. | To empower communities and regenerating neighbourhoods | Hedland Community Safety Advisory Forum | High | 2017-12-12 | 2018-02-05 | 2018-02-23 | closed
| 2 | Working groups in Port Hedland | Provide a list of working groups in Port Hedland. Outline their objectives and core functioning. | COMPLETED | To empower communities and regenerating neighbourhoods | Town of Port Hedland | Medium | 2017-12-12 | 2018-02-05 | 2018-02-05 | closed
| 3 | Adopt common terminology "Aboriginal" to the Advisory Forum | Maureen Kelly requested the Advisory Forum Adopt Aboriginal as a shared common language in the Advisory Forum when talking about Aboriginal people and communities and not referring to them as, Indigenous. | Supported by Hedland Community Safety Advisory Forum | Community Safety and Crime Prevention Plan | Hedland Community Safety Advisory Forum | High | 2017-12-12 | 2017-12-12 | 2017-12-12 | closed
| 4 | Native Title Groups | Research and list all native title groups and trustees in the Hedland region. | COMPLETED | To empower communities and regenerating neighbourhoods | Town of Port Hedland | Low | 2017-12-12 | 2018-02-05 | 2018-02-05 | closed
| 5 | Youth Council | Identify a platform for sub working groups i.e. youth council to have an advisory component to the Forum. | Term of reference drafted for a potential Hedland Youth Council. | To empower communities and regenerating neighbourhoods | Town of Port Hedland | Low | 2017-12-12 | 2018-02-05 | 2018-02-05 | closed
| 6 | Community Safety and Crime Prevention Plan | Review and update the Community Safety and Crime Prevention Plan | COMPLETED, RFQ released and expires Wednesday 14 February 2018. | Community Safety and Crime Prevention Plan | Town of Port Hedland | Urgent | 2017-12-12 | 2018-01-15 | 2018-01-22 | closed
| 7 | Email by Maureen Kelly received 2 Feb 18 | • Data on the Professor Roz Walker report on health of kids in the Pilbara. • Invite the CEO of Wirraka Maya, June Councillor to present on FASD in Hedland. Wirraka Maya • Information on what programs are in place to address kids and parents with health issues from alcohol and drugs. • Data on the number of dialysis patients in Hedland. WA Country Health Services • Data on the number of deaths in Hedland from alcohol and drugs and suicides. WA Country Health Services • Data on the number of court charges and hospital admission from alcohol and drugs. WA Country Health Services • Stats on how many kids are not attending school or not engaged in any form of education. Department of Education | Followed up in next meeting 30 April 2018 | Community Safety and Crime Prevention Plan | Hedland Community Safety Advisory Forum | Medium | 2018-02-02 | 2018-02-15 | 2018-02-26 | closed
| 8 | AOD-VSU data outcomes and analysis | Please note once the plan has expired it is lodged with the Mental Health Commission. The working group responsible for this plan review the KPI's set then the backbone organisation (Bloodwood Tree) then submits the review to MHC. These plans are not lodged with the State Parliament. | Community Safety Advisor spoke with Mental Health Commission | Port Hedland AOD-VSU Plan | Kevin Michel MLA | High | 2018-02-26 | 2018-04-09 | 2018-03-29 | closed
| 9 | Advocate for s152 data | Kevin Michel to support the Police in gaining the s152 data from WAPOL with support Dept of Communities, UWA police statistical data, outlining success, progress and outcomes. | Kevin Michel MLA office submitted letter to WAPOL minister, awaiting feedback. | To empower communities and regenerating neighbourhoods | Kevin Michel MLA | Medium | 2018-02-26 | 2018-04-09 | 2018-04-09 | closed
| 10 | FASD Data | FASD reasearch in the Pilbara to be presented. | Completed | To support families, children and young people | University of Western Australia | Low | 2018-02-26 | 2018-04-09 | 2018-04-09 | closed
| 11 | Mapping of safe houses/ diversonary houses/ residential settings | Safe Houses and Diversionary Houses | Completed | To support families, children and young people | Town of Port Hedland | High | 2018-02-26 | 2018-04-09 | 2018-04-16 | closed
| 12 | Corporate Social Responsibility (CSR) | 15 minute presentation each. What is your businesses CSR? Does it meet community expectation? How do you measure it? Why did your organisation start doing these initatives? If you have a powerpoint presentation, please forward to kbooth@porthedland.wa.gov.au | Completed | To empower communities and regenerating neighbourhoods | Industry: Roy Hill, BHP, Rio Tinto & FMGL | Low | 2018-02-26 | 2018-04-09 | 2018-04-09 | closed
| 13 | Welfare Cards | Presentation on the different welfare card management systems. Cashless Debit Card & Basics Card. TOPH to collate information on Takeaway Management System (TAMS). | In progress- CSA contacted Wyndham Kununarra Liquor Accord for TAMS info. | To identify and tackle priority offences in Port Hedland | Department of Social Services & Department of Human Services | Medium | 2018-02-26 | 2018-04-09 | 2018-04-16 | closed
| 14 | s64 application- Pilbara | A majority vote, agreed with the s64 support. AMENDMENT: All members interested in supporting s64 are to submit their letter to Racing, Gaming and Liquor individually. Further information on s64 can be found in the unconfirmed minutes. | Closed | To reduce repeat offending | Hedland Community Safety Advisory Forum | Low | 2018-02-26 | 2018-04-09 | 2018-02-28 | closed
| 15 | Community Perception Survey & Alcohol Managament Survey Data | Town of Port Hedland to feedback data from the Alcohol Managemant Survey completed in 2017, alongside the Bloodwood Tree Community Perception Survey's released annually. | Completed | To empower communities and regenerating neighbourhoods | Town of Port Hedland | Medium | 2018-02-26 | 2018-04-09 | 2018-03-28 | closed
| 16 | Governance Review | Review the following: A) Terms of reference B) Proposed governance structure C) Evaluate membership inclusion of Hedland Collective Co-ordinator. Terms of reference will be evaluated by the group. Under the current Terms of Reference the Chairperson and Community Safety Advisor decide on the appointment of members, with advice provided by the Forum to inform their decision.This will increase the membership to 17 representatives. | Online Form sent to members | Community Safety and Crime Prevention Plan | Hedland Community Safety Advisory Forum | Urgent | 2018-04-30 | 2018-05-21 | 2018-06-11 | closed
| 18 | West Pilbara Healing Plan | Kevin Michel to update group on West Pilbara Operations in Roebourne and what planning is taking place for the rest of the Pilbara from State Government. | Item, has been reallocated to Dept Communities and they will provide an update in the West Pilbara and Port Hedland region. | To support families, children and young people | Department of Communities | High | 2018-04-30 | 2018-08-14 | 2018-08-14 | closed
| 19 | 2 Mile | TOPH to provide an update of stage one of the 2 Mile clean up restoration project | Pre-reading update of the 2 Mile project attached to agenda | To empower communities and regenerating neighbourhoods | Town of Port Hedland | Low | 2018-04-30 | 2018-08-14 | 2018-08-14 | closed
| 21 | Terms of Reference- update | Edit document to cleary outline its autnomous role from Council. Send to Advisory Forum 2 weeks prior to next meeting, to provide feedback before adoption at meeting. Amendments to Scope and Objectives | In progress | Good Governance and Civic Leadership | Town of Port Hedland | High | 2018-06-11 | 2018-08-07 | 2018-08-21 | closed
| 22 | Hedland Collective | Formalising a communciation framework with Hedland Collective | In progress | Good Governance and Civic Leadership | Town of Port Hedland | Low | 2018-06-11 | 2018-08-14 | 2018-08-14 | closed
|  |  | Current Advisory Forum Members agreed to report back to the group who are representatives of the Hedland Collective working groups, pertaining to relevant Community Safety discussions | Agreement | Good Governance and Civic Leadership | Hedland Community Safety Advisory Forum | High | 2018-06-11 | 2018-06-11 | 2018-06-11 | closed
| 23 | Governance Structure | Revised Governance Structure to be completed and presented back to Advisory Forum for adoption at next meeting. | Adopted 21 August 2018 | Good Governance and Civic Leadership | Town of Port Hedland | High | 2018-06-11 | 2018-08-14 | 2018-08-21 | closed
| 28 | Minute Adoption of previous meeting June 2018 | Moved: Margi Faulkner Seconded: lincoln Tavo | Completed | Good Governance and Civic Leadership | Hedland Community Safety Advisory Forum | Low | 2018-08-21 | 2018-08-21 | 2018-08-21 | closed
50

## (AG) Action Register
Hedland Community Safety Action Group
ACTION REGISTER |  |  |  | Count of entries (filter) | 8 |  | Today | 2018-09-03 | Last entry | 2018-08-22
No. | Action point | Description | Status / ongoing activities | Startegic Goal | Owner / responsibility | Priority | Date identified | Due date | Date closed | Status
1 | Governance | Group identified no need for a terms of reference. | Completed | Good Governance and Civic Leadership | Hedland Community Safety Action Group | Low | 2018-08-02 | 2018-08-27 | 2018-08-02 | closed
2 | Membership | Extend membership to the following: WAPOL (Community Engagement Team), Ashburton Aboriginal Corporation, CaLD, CPFS & Aged Care. | Completed | Good Governance and Civic Leadership | Town of Port Hedland | High | 2018-08-02 | 2018-08-27 | 2018-08-21 | closed
3 | Mission Statement | Brain storm mission statement ideas for next meeting, discussions on the following statements. "Our Community", "Your Community, Our Community". A statement that outlines the diversification of the community including FIFO population in which everyone takes responsibility for safety in community. Discussion notes: The Hedland community is one where people are able to enjoy a safe and secure environment. | In progress | Community Safety Plan | Hedland Community Safety Action Group | Medium | 2018-08-02 | 2018-09-05 |  | due in 9 days
4 | Communication Framework | How will the Advisory Forum and Action Group communicate with each other and work collaborativley. The group identified there would need to be a communication framework. Suggestions of a modified ToPH Council Agenda template would be constructed and fedback to the group at the next meeting and be discussed with the Advisory Forum. | In progress | Good Governance and Civic Leadership | Town of Port Hedland | Medium | 2018-08-02 | 2018-08-29 |  | due in 2 days
5 | Meeting Dates for 18/19 | AF identified the need to collate meeting dates for working groups, community forums/ meetings to reduce duplication of meetings on same days. All stakeholders to provide Community Safety Advisor with meeting dates to add to the meeting dates tab in this document. Document will be uploaded to the Community Safety tab on the Town's website and be uploaded weekly. | In progress | Good Governance and Civic Leadership | Action Group | High | 2018-08-20 | 2018-09-05 |  | due in 2 days
6 | Proxy Nomination | Can all members please nominate a proxy. Details to be added to the Contact List tab | In progress | Good Governance and Civic Leadership | Action Group | Low | 2018-08-21 | 2018-09-05 |  | due in 2 days
| s52 potential addresses (AF) | The group to discuss potential houses that are not listed under s52 Liquor Restricted Premises 'Dry Houses'. The AF would like to advocate for at risk places that have not applied due to personal/ cultural barriers, access or limitation to applying. Future consideration of addresses. | In progress- to be discussed at the next meeting. | To support families, children and young people | Action Group | Medium | 2018-08-22 | 2018-09-05 |  | due in 2 days
| Banned Drinkers Register | AF wants to know what the Action Group thinks about how the roll out of a Banned Drinkers Register will look for the Pilbara but in particular the Hedland community support services. What is working well for 'problematic drinkers', are rap-around practices occuring within case management, what are the gaps of servicing this target audience. | In progress | Good Governance and Civic Leadership | Action Group | Medium | 2018-08-21 | 2018-09-05 |  | due in 2 days

## Attendance Register 2018
ATTENDANCE REGISTER
Advisory Forum Membership |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  | Mayor Blanco | BHP Billiton- Chris Dark | RIO Tinto- Biro Diallo | FMGL- Fernando Peirera | Roy Hill- Julian Hill | UWA- Harry Blagg | Kevin Michel- WA State Parliament | Dept. Communities- Natasha Bargeus | Dept. Social Services- Tanya George | Dept. Human Services- Melissa Rennie | Dept.Education- Neil Darby | Hedland Strong Leaders- Alfred Barker & Maureen Kelly | WAPOL- Jayd Morawski | WA Country Health Services-Margi Faulkner | Dept. Corrective Services- Paula Hyde | Prime Minister and Cabinet- David Pedler
Meeting date | 2017-12-12 | 1: Non-voting participants in attendance: (TOPH) David Pentz, Cr Hebbard, Cr Daccache, Keesha Booth, Michael Cuvalo, (Facilitator) Dorinda Cox.
Attendance statues | Y/N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Yx2 | Yx2 | N | N/A | Y
Proxy | Y/N | 4: Y- Lincoln Tavo; 5: Y-Jeanette Haselby; 9: Y- Julie Flux; 10: Y- Helen Brahim; 14: N- DNA; 15: N/A; 16: Y- Merle-Ann Cochrane
Comment |  | Agenda item 1.1 N/A | Agenda item 1.1 received | Agenda item 1.1 received | Agenda item 1.1 received | Agenda item 1.1. received | Agenda item 1.1 N/A | Agenda item 1.1 N/A | Agenda item 1.1 received | Agenda item 1.1 received | Agenda item 1.1 N/A | Agenda item 1.1 received | Agenda item 1.1 N/A | Agenda item 1.1 received |  | N/A | Agenda item 1.1. received
ATTENDANCE REGISTER
Advisory Forum Membership |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  | Town of Port Hedland- Elected Member | BHP Billiton- Chris Dark | RIO Tinto- Biro Diallo | FMGL- Fernando Peirera | Roy Hill- Julian Hill | UWA- Harry Blagg | Kevin Michel- WA State Parliament | Dept. Communities- Natasha Bargeus | Dept. Social Services- Tanya George | Dept. Human Services- Melissa Rennie | Dept.Education- Neil Darby | Hedland Strong Leaders- Alfred Barker & Maureen Kelly | WAPOL- Jayd Morawski | WA Country Health Services-Margi Faulkner | Dept. Corrective Services- Paula Hyde | Prime Minister and Cabinet- David Pedler
Meeting date | 2018-02-26 | 1: Non-voting participants in attendance: Dorinda Cox (Facilitator), (TOPH) David Pentz, Michael Cuvalo, Keesha Booth, Justine Esmonde Cr Whitwell, Cr Pitt, Laura Liddle & Kathy McGrath (Youth Justice), Vicky-Tre Stevens (YIC), Stephanie Holmes (Mission Australia), Timara Simpson (Bloodwood Tree Inc).
Attendance statues | bar: 1 to 16
Proxy |  | 2: Y- Nicole Del Borello; 3: Y- Nathan Douglas; 4: Y- Lincoln Tavo; 5: Y- Jeanette Hasleby; 9: N; 11: Y- Joanne Harris via phone 0400209772.; 16: N
Comment |  | 5: Teleconference; 6: Additional guest: Joe Clare; 9: Apologies; 16: Apologies
Advisory ForumMembership |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  | Town of Port Hedland- Mayor Blanco | BHP Billiton- Chris Dark | RIO Tinto- Nathan Douglas | FMGL- Lincoln Tavo | Roy Hill- Julian Hill | UWA- Harry Blagg | Kevin Michel- WA State Parliament | Dept. Communities- Natasha Bargeus | Dept. Social Services- Julie Flux | Dept. Human Services- Melissa Rennie | Dept.Education- Neil Darby | Hedland Strong Leaders- Alfred Barker & Maureen Kelly | WAPOL- Jayd Morawski/Allan Jane | WA Country Health Services-Margi Faulkner | Dept. Corrective Services- Paula Hyde | Prime Minister and Cabinet- David Pedler
Meeting date | 2018-04-30 | 1: Non votiving participants/ guests: Dorinda Cox (Facilitator), (TOPH) David Pentz, Michael Cuvalo, Keesha Booth, Armando De La Florivade, Cr Whitwell, Karen Munro (Chairperson-Hedland Youth Stakeholder Action Group), Lyell Morrison (Regional Manager- Pilbara Youth Justice), Brent Rudler (Port Hedland Liquor Accord), Justine Munro (JD Hardie), Rebeka Worthington (Well Women's), Gabrielle Marks (Hedland Women's Refuge), June Councillor (CEO, Wirraka Maya)
Attendance statues | Y/N | bar: 1 to Apologies 16
Proxy | Y/N | 3: Y-Nathan Douglas (Operations Manager); Teleconference 5: Y- Jeanette Haselby (Manager Community Development); Additional guest: Joe Clare 6: Additional Guest: Joe Clare (Senior Lecturer); Apologies 10: Additional guest: South Hedland Service Centre Manager – Faizah Ghufron.; Apologies 12: Apologies Maureen Kelly; Apologies 16: Y- Merle Ann Cochrane
Advisory Forum Membership |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  | Town of Port Hedland- Mayor Blanco | BHP Billiton- Chris Cottier | RIO Tinto- Nathan Douglas | FMGL- Lincoln Tavo | Roy Hill- Jeanette Hasleby | UWA- Harry Blagg | Kevin Michel- WA State Parliament | Dept. Communities- Natasha Bargeus | Dept. Social Services-Julie Flux | Dept. Human Services- Faizah Ghufron | Dept.Education- Neil Darby | Hedland Strong Leaders- Alfred Barker & Maureen Kelly | WAPOL- Jayd Morawski/Allan Jane | WA Country Health Services-Margi Faulkner | Dept. Corrective Services- Paula Hyde | Prime Minister and Cabinet- Melissa Rennie
Meeting date | 2018-06-11 | 1: Non votiving participants/ guests: Dorinda Cox (Facilitator), Town of Port Hedland: David Pentz (CEO),Michael Cuvalo (Manager Environmental Health & Community Safety), Keesha Booth (Community Safety Advisor), Armando de la Olivade (Senior Partnerships and Engagement Officer)
Attendance statues | Y/N | Y | Y | N | Y | Y | N | N | - | Y | Y | Y | Y | Y | Y | Y | N
Proxy | 2018-06-11 Y/N: Y/N; Non votiving participants/ guests: Dorinda Cox (Facilitator), Town of Port Hedland: David Pentz (CEO),Michael Cuvalo (Manager Environmental Health & Community Safety), Keesha Booth (Community Safety Advisor), Armando de la Olivade (Senior Partnerships and Engagement Officer) N: Apologies; Non votiving participants/ guests: Dorinda Cox (Facilitator), Town of Port Hedland: David Pentz (CEO),Michael Cuvalo (Manager Environmental Health & Community Safety), Keesha Booth (Community Safety Advisor), Armando de la Olivade (Senior Partnerships and Engagement Officer) N: Apologies; Non votiving participants/ guests: Dorinda Cox (Facilitator), Town of Port Hedland: David Pentz (CEO),Michael Cuvalo (Manager Environmental Health & Community Safety), Keesha Booth (Community Safety Advisor), Armando de la Olivade (Senior Partnerships and Engagement Officer) N: Proxy: Tricia Hebbard; Non votiving participants/ guests: Dorinda Cox (Facilitator), Town of Port Hedland: David Pentz (CEO),Michael Cuvalo (Manager Environmental Health & Community Safety), Keesha Booth (Community Safety Advisor), Armando de la Olivade (Senior Partnerships and Engagement Officer) -: Did not attend; Non votiving participants/ guests: Dorinda Cox (Facilitator), Town of Port Hedland: David Pentz (CEO),Michael Cuvalo (Manager Environmental Health & Community Safety), Keesha Booth (Community Safety Advisor), Armando de la Olivade (Senior Partnerships and Engagement Officer) Y: Apologies: Jayd Morawski; Non votiving participants/ guests: Dorinda Cox (Facilitator), Town of Port Hedland: David Pentz (CEO),Michael Cuvalo (Manager Environmental Health & Community Safety), Keesha Booth (Community Safety Advisor), Armando de la Olivade (Senior Partnerships and Engagement Officer) N: Apologies
ATTENDANCE REGISTER
Action Group Membership |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  | Town of Port Hedland-Michael Cuvalo | University of Western Australia- Harry Blagg | Port Hedland Alcohol & Other Drug Management Group- Kelly Howlett | Eary Years Network- Yasmina Smith | Hedland Aboriginal Strong Leaders- Maureen Kelly | Domestic & Family Violence- Hedland's Women's Refuge | Hedland Collective | FASD Reference Group | Hedland Aboriginal Health Planning Forum | Port Hedland Chamber of Commerce | Hedland Youth Stakeholder Action Group- Karen Munro | Culturally and Linguistically Diverse- PCLS | N.D.I.S | Aged Care- WACHS | Ashburton Aboriginal Corporation | Dept. Communities-CPFS
Meeting date | Meeting date | 1: 2018-08-02; 2: Facilitator- Dorinda Cox, Keesha Booth (ToPH)
Attendance statues | Attendance statues |  | Y | Y | Y | Y | Y | Y | Y | Y | N | N | Y | - | - | - | - | -
Proxy | Proxy
| Comment | 10: Apologies; 11: Apologies
Advisory Forum Membership |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  | Town of Port Hedland- Mayor Blanco | BHP Billiton- Chris Cottier | RIO Tinto- Nathan Douglas | FMGL- Lincoln Tavo | Roy Hill- Jeanette Hasleby | UWA- Harry Blagg | Kevin Michel- WA State Parliament | Dept. Communities- Natasha Bargeus | Dept. Social Services-Julie Flux | Dept. Human Services- Faizah Ghufron | Dept.Education- Neil Darby | Hedland Strong Leaders- Alfred Barker & Maureen Kelly | WAPOL- Jayd Morawski/Allan Jane | WA Country Health Services-Margi Faulkner | Dept. Corrective Services- Paula Hyde | Prime Minister and Cabinet- Melissa Rennie
Meeting date | 2018-06-11 | 1: Non votiving participants/ guests: Dorinda Cox (Facilitator), Town of Port Hedland: David Pentz (CEO),Michael Cuvalo (Manager Environmental Health & Community Safety), Keesha Booth (Community Safety Advisor), Armando de la Olivade (Senior Partnerships and Engagement Officer), Justine Esmonde (Senior Youth Officer-JD Hardie), Vicky Tree-Stevens (Youth Involvement Council), Tim Turner (Dept. Communities), Samantha McMeekin (BHP)
Attendance statues | Y/N | bar: 1 to Apologies 16
Proxy | Y/N | 2: Y- Nicole Del Borello; 3: Did not attend; 5: Apology; 6: Apologies; 7: Apology; 9: Y- Peter Ryan; Apologies 10: Apology; Apologies 11: Y- Michael Jennings; Apologies 13: Apology- Allan Jane

## Meeting Dates 18-19
Colour Code |  | Public Holidays | Scheduled Meeting | Meeting to be confirmed | School Holidays | Events that can impact community safety (-/+) |  |  |  | Abbreviation | Name | General Time of meetings
Monday date | Week | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |  | Advisory Forum | Hedland Community Safety Advisory Forum | 9:30am-1:00pm
2018-01-01 | 1 | PH | [7 empty] | Action Group | Hedland Community Safety Action Group | 9:00am-12:00pm
2018-01-08 | 2 | [8 empty] | PHAODMG | Port Hedland Alcohol Other Drug Management Group | 10:00am-11:00am
2018-01-15 | 3 | [8 empty] | OCM | Ordinary Council Meeting | 5:30pm
2018-01-22 | 4 |  |  | OCM |  | PH |  |  |  | DLG | District Leadership Group (Dept. Communities)
2018-01-29 | 5 | [8 empty] | HYSAG | Hedland Youth Stakeholder Action Group | 10:00am-11:00am
2018-02-05 | 6 | [8 empty] | Early Years Network | Hedland Early Years Network Meeting
2018-02-12 | 7 |  | PHCCI (BAH) | [6 empty] | CPC LAC | Child Parent Centre LAC Meeting
2018-02-19 | 8 | [8 empty] | LEMC | Local Emergency Management Committee
2018-02-26 | 9 | Advisory Forum | HYSAG | OCM & PHCCI (BBS) | [5 empty] | HC | Hedland Collective
2018-03-05 | 10 |  |  |  | International Women's Day |  |  |  |  | PHCCI (BBS) | Port Hedland Chamber of Commerce and Industry- Business Breakfast Series
2018-03-12 | 11 |  | PHCCI (BAH) |  |  | PHAODMG |  |  |  | PHCCI (BAH) | Port Hedland Chamber of Commerce and Industry- Business After Hours
2018-03-19 | 12 | [8 empty] | Roadwise
2018-03-26 | 13 |  |  | OCM & PHCCI (BBS) | [5 empty] | HASL | Hedland Aboriginal Strong Leaders
2018-04-02 | 14 | [8 empty] | ATSI Forum | Aboriginal and Torres Strait Islander Forum
2018-04-09 | 15 |  | PHCCI (BAH)
2018-04-16 | 16 |  |  | PHCCI (BBS)
2018-04-23 | 17 | OCM |  | PH
2018-04-30 | 18 | Advisory Forum
2018-05-07 | 19 |  | PHCCI (BAH)
2018-05-14 | 20 | Yule River Bush Meeting
2018-05-21 | 21 |  |  | OCM/ PHCCI (BBS)
2018-05-28 | 22
2018-06-04 | 23 | PH
2018-06-11 | 24 | Advisory Forum | PHCCI (BAH)
2018-06-18 | 25 |  |  |  |  | PHCCI (BBS)
2018-06-25 | 26 |  |  | OCM
2018-07-02 | 27
2018-07-09 | 28 |  | PHCCI (BAH)
2018-07-16 | 29 |  | Early Years Network
2018-07-23 | 30 |  | CPC LAC | OCM/ PHCCI (BBS) |  | White Ribbon Night
2018-07-30 | 31
2018-08-06 | 32
2018-08-13 | 33 |  | PHCCI (BAH)
2018-08-20 | 34 |  |  | OCM/ PHCCI (BBS) |  |  | North West Festival | North West Festival
2018-08-27 | 35 | Pilbara Community Cabinet Meeting | HYSAG |  | PHAODMP | Supportive Hedland (HC) | Newman Outback Fusion Festival * Broome Shinju Festival | Newman Outback Fusion Festival * Broome Shinju Festival
2018-09-03 | 36 |  |  | Action Group |  | FASD Awareness Day (South Hedland CBD) | Local AFL Grandfinal
2018-09-10 | 37 |  | PHCCI (BAH) |  | Vibrant Hedland (HC)
2018-09-17 | 38 |  |  |  | Form Pilbara Creative & Cultural Forum (Newman) | Form Pilbara Creative & Cultural Forum (Newman) | Cockatoo Classic Fishing Competition | Cockatoo Classic Fishing Competition
2018-09-24 | 39 |  | HYSAG & FASD Network Meeting | OCM & Resources Sub-working Group & Pathways to Opportunity (HC) TBC/ PHCCI (BBS) |  | ATSI Forum | AFL GRANDFINAL | NRL GRANDFINAL
2018-10-01 | 40 |  |  |  | Dept. Communities Homelessness Consultation
2018-10-08 | 41 |  | PHCCI (BAH) |  |  | DLG (Karratha) |  |  | Mental Health Week
2018-10-15 | 42 |  |  |  | PHAODMP & LEMC |  | Oktoberfest Blanche Bar
2018-10-22 | 43 |  | Advisory Forum | OCM/ PHCCI (BBS)- TBC |  | Vibrant Hedland (HC)
2018-10-29 | 44 |  | HYSAG | Action Group
2018-11-05 | 45 |  |  | Resources Sub Working Group & Pathways to Opportunity (HC)
2018-11-12 | 46 |  |  |  | LG Community Safety Network Meeting (Perth)
2018-11-19 | 47 | [6 empty] | White Ribbon Day
2018-11-26 | 48 |  | HYSAG | OCM
2018-12-03 | 49 | International Day of people with a Disability | Advisory Forum | Action Group | Vibrant Hedland (HC)
2018-12-10 | 50 |  |  |  | PHAODMP/ PHCCI (BAH)- TBC
2018-12-17 | 51 |  |  |  |  | Pathways to Opportunity (HC)
2018-12-24 | 52 |  | PH | PH |  | PHCCI (BBS)
2018-12-31 | 1 |  | PH | PH
Formulas:
Colour Code = [Colour Code, row above]+7

## Group Membership
Heldand Community Safety Advisory Forum
1 | Local Government | Town of Port Hedland
2 | Industry | BHP
3 |  | FMGL
4 |  | Roy Hill
5 |  | Rio Tinto
6 | Local Aboriginal Leadership Group | Hedland Aboriginal Strong Leaders
7 | State Government | Department of Education- Pilbara
8 |  | Department of Justice
9 |  | WA Police
10 |  | Department of Communities
11 |  | Department of Health
12 |  | Member for Pilbara
13 | Federal | Department of Prime Minister and Cabinet
14 |  | Department of Social Services
15 |  | Department of Human Services
16 | Research Body | University of Western Australia
Hedland Community Safety Action Group
1 | Local Government | Town of Port Hedland
2 | Local Drug Action Team (LDAT) | Port Hedland Alcohol and Other Drug Management Plan Group
3 | Collective Impact | Hedland Collective
4 | Disability | National Disability & Insurance Scheme
5 | Research Body | Univeristy of Western Australia
6 | Health and Aged Care | WA Country Health Services
7 | Social Services | WA Council of Social Services
8 | Police | WA Police- Community Engagement
9 | Local Aboriginal Leadership Group | Hedland Aboriginal Strong Leaders
10 | Employment | Ashburton Aboriginal Corporation
11 | Early Years | Early Years Network
12 |  | Department of Communities
13 | Aboriginal Medical Services | Pilbara Aboriginal Health Planning Forum
14 | CaLD or Family & Domestic Violence | Hedland Women's Refuge
15 |  | Pilbara Community Legal Services
16 | Youth | Hedland Youth Stakeholder Action Group
17 |  | Headspace- Pilbara

## Control
Input parameter and lists for action point register
Status marked yellow if time till due date is <= |  | 10
Project Start |  | 2017-12-12
Project End |  | 2021-12-12
Priority | Resources | Strategic Goal
Low | Action Group | To support families, children and young people
Advisory Forum
Medium | WAPOL, CPFS, Hedland Aboriginal Strong Leaders | To empower communities and regenerating neighbourhoods
High | Sub-group | To identify and tackle priority offences in Port Hedland
Urgent | Dept. Communities- CPFS | To reduce repeat offending
| Dept. Education- Pilbara | To design out crime using technology
Community Safety and Crime Prevention Plan
Port Hedland AOD-VSU Plan
Good Governance and Civic Leadership

## Compatibility Report
Compatibility Report for Action Register.xls
Run on 13/12/2017 10:33
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Significant loss of functionality | # of occurrences | Version
Some cells have overlapping conditional formatting ranges. Earlier versions of Excel will not evaluate all of the conditional formatting rules on the overlapping cells. The overlapping cells will show different conditional formatting. | 1
| Action Point Register'!J5 | Excel 97-2003
One or more cells in this workbook contain a conditional formatting type that is not supported in earlier versions of Excel, such as data bars, color scales, or icon sets. | 1
| Action Point Register'!J5 | Excel 97-2003